## Gantt Chart
GANTT CHART
PROJECT TITLE |  | A Voice Controlled and Gesture-Based Robot |  | NAME | Daniel Ang
2026-09-28
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
Number | TASK TITLE | START DATE | END DATE | Notes | TARGET DURATION | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
 | time axis 2026-09-28 to 2026-11-27
1 | Obtaining items and quality check | 2026-09-28 | 2026-10-01 | Before start of trimester/part b | 4 days
Phase 1 | Hardware configuration and setup/Robot design | 2026-09-28 | 2026-10-16 |  | 3 weeks
2 | 3D print parts | 2026-09-28 | 2026-10-09 |  | 10 days
3 | Raspberry Pi Pin allocation | 2026-09-30 | 2026-10-07 |  | 6 days
4 | Wiring Circuit and Assembly | 2026-10-05 | 2026-10-16 |  | 10 days
Phase 2 | Software Configuration | 2026-10-12 | 2026-11-13 |  | 5 weeks | bar: 2026-09-28 to 2026-10-09
5 | L298N Motor Driver Code Configuration | 2026-10-12 | 2026-10-23 | Basic Obstacle avoidance | 10 days
6 | Ultrasonic Sensor Code Configuration | 2026-10-12 | 2026-10-23 | Basic Obstacle Avoidance | 10 days
7 | Microphone/Speaker Code Configuration | 2026-10-12 | 2026-11-06 | Voice Recognition | 20 days
8 | Camera and Pi Hat Configuration | 2026-10-19 | 2026-11-06 | Gesture Recognition | 15 days
9 | Designing user interface on Visual Studio | 2026-10-26 | 2026-11-06 |  | 10 days
10 | Testing and Debugging of Robot | 2026-11-02 | 2026-11-13 |  | 10 days
Phase 3 | Consolidation | 2026-11-09 | 2026-11-25 |  | 2.6 weeks | bar: 2026-09-28 to 2026-11-06
11 | Final testing and troubleshooting of Robot | 2026-11-09 | 2026-11-18 |  | 8 days
12 | Video Recording of Robot Operation | 2026-11-16 | 2026-11-20 |  | 5 days
13 | Project Documentation | 2026-11-09 | 2026-11-25 | Final Project Report | 13 days
14 | Final presentation preparation | 2026-11-18 | 2026-11-25 | Final presentation 25 Nov | 6 days
Legend / notes
Edit only the blue cells: project start (C4), final presentation (F4) and each task's START / END DATE. Bars, phase dates and durations update automatically.
Dark grey bar = phase span (earliest start to latest end of its tasks). Blue bar = task.
Assumption: the original 12-week template was compressed to 9 weeks (28 Sep to 25 Nov 2026); task dates are proposed and can be adjusted. Task 14 (final presentation prep) was added.
Duration counts working days (Mon-Fri). Project title is a placeholder; edit C3.
Formulas:
Daniel Ang = NETWORKDAYS([START DATE],[END DATE])&" days"
Daniel Ang = ROUND(NETWORKDAYS([START DATE],[END DATE])/5,1)&" weeks"
START DATE = MIN([START DATE, row below]:C13)
END DATE = MAX([END DATE, row below]:D13)